## Phase 1
Revision: 21 june 2018 by Roar Pedersen
ACTIVITIES, BUDGET, FINANCING AND WORK SCHEDULE
One separate form to be filled in for each phase of work, but use the same work book
Write only in blue cells
Title |  | Example: Development of…
Phase of work |  | Example Phase 1:
Year and cost distribution [%]
| Last revision | 2018-04-14 | [5 empty] | 2018 | 20
| Prepared by | Petter Ola Hanssen |  |  | Tlf: | 48099548 |  | 2019 | 40
[8 empty] | 2020 | 40
[8 empty] | 2021 | 0
[8 empty] | Control | 100
Participants |  | Company A | Company B | Company C
Contact person
Phone
Mail
Hourly rate [NOK] |  | 700 | 700 | 700
Activity plan with hour budget |  | Company A | Company B | Company C | 0 | 0 | 0 | 0 | 0 | Total
| Activities | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours
1.1 | Example: Consept development | 200 | 100 | 50 | 0 | 0 | 0 | 0 | 0 | 350
1.2 | Example: Engineering | 100 | 300 | 50 | 0 | 0 | 0 | 0 | 0 | 450
1.3 | Example: Price calculation | 50 | 300 | 50 | 0 | 0 | 0 | 0 | 0 | 400
1.4 | Example: Cost/benefit analysis | 50 | 100 | 50 | 0 | 0 | 0 | 0 | 0 | 200
1.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.9 | Project management and reporting | 50 | 50 | 150 | 0 | 0 | 0 | 0 | 0 | 250
| Sum | 450 | 850 | 350 | 0 | 0 | 0 | 0 | 0 | 1650
Activity plan with cost budget |  | Company A | Company B | Company C | 0 | 0 | 0 | 0 | 0 | Total
| Activities | NOK | NOK | NOK | NOK | NOK | NOK | NOK | NOK | NOK
1.1 | Example: Consept development | 140000 | 70000 | 35000 | 0 | 0 | 0 | 0 | 0 | 245000
1.2 | Example: Engineering | 70000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 315000
1.3 | Example: Price calculation | 35000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 280000
1.4 | Example: Cost/benefit analysis | 35000 | 70000 | 35000 | 0 | 0 | 0 | 0 | 0 | 140000
1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.9 | Project management and reporting | 35000 | 35000 | 105000 | 0 | 0 | 0 | 0 | 0 | 175000
| Travel costs | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 30000
| Material costs prototype (separate specification) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Subcontracting prototype (separate specification) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Value of raw material to be destroyed after tests | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other costs (separate specification) | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 15000
| Sum | 330000 | 610000 | 260000 | 0 | 0 | 0 | 0 | 0 | 1200000
| Percentage distribution of costs | 27.5% | 50.83% | 21.67% | 0% | 0% | 0% | 0% | 0% | 100%
|  | FINANCING |  |  |  | Financing |  | Costs
[6 empty] | T | E | L | R | A |  | Distribution | Distribution
|  |  | Participants | Distribution | Own efforts | Grants | Own effort | Wages | Travel | Other |  | grants | grants
|  |  |  | of grants [%] | [%] | [NOK] | [NOK] | [NOK] | [NOK] | [NOK] |  | [NOK] | [%]
|  | 2018 | FHF | 100 |  | 120000
|  |  | IN | 0 |  | 0
|  |  | NFR | 0 |  | 0
| in Cell F68 the sum should always be 100 |  | Control | 100
|  |  | Company A |  | 50 |  | 33000 | 63000 | 2000 | 1000 |  | 33000 | 27.5
|  |  | Company B |  | 50 |  | 61000 | 119000 | 2000 | 1000 |  | 61000 | 50.8333
|  |  | Company C |  | 50 |  | 26000 | 49000 | 2000 | 1000 |  | 26000 | 21.6667
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 100
|  | 2019 | FHF | 100 |  | 240000
|  |  | IN | 0 |  | 0
|  |  | NFR | 0 |  | 0
|  |  | Control | 100
|  |  | Company A |  | 50 |  | 66000 | 126000 | 4000 | 2000 |  | 66000 | 27.5
|  |  | Company B |  | 50 |  | 122000 | 238000 | 4000 | 2000 |  | 122000 | 50.8333
|  |  | Company C |  | 50 |  | 52000 | 98000 | 4000 | 2000 |  | 52000 | 21.6667
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 100
|  | 2020 | FHF | 100 |  | 240000
|  |  | IN | 0 |  | 0
|  |  | NFR | 0 |  | 0
|  |  | Control | 100
|  |  | Company A |  | 50 |  | 66000 | 126000 | 4000 | 2000 |  | 66000 | 27.5
|  |  | Company B |  | 50 |  | 122000 | 238000 | 4000 | 2000 |  | 122000 | 50.8333
|  |  | Company C |  | 50 |  | 52000 | 98000 | 4000 | 2000 |  | 52000 | 21.6667
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 100
|  | 2021 | FHF | 100 |  | 0
|  |  | IN | 0 |  | 0
|  |  | NFR | 0 |  | 0
|  |  | Control | 100
|  |  | Company A |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | Company B |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | Company C |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0! | #DIV/0!
|  |  | Sum |  |  | 600000 | 600000 | 1155000 | 30000 | 15000 |  | 600000
|  |  | Sum grants and own effort |  |  | 1200000 | (grants + own effort)
|  |  | Sum costs |  |  | 1200000 | (wages + travel costs + other costs))
|  |  | Public support |  |  | 50%
Work Shecule
| Activities | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021
|  | 1 quarter | 2 quarter | 3 quarter | 4 quarter | 1 quarter | 2 quarter | 3 quarter | 4 quarter | 1 quarter | 2 quarter | 3 quarter | 4 quarter | 1 quarter | 2 quarter | 3 quarter | 4 quarter
1.1 | Example: Consept development |  |  |  | X | X
1.2 | Example: Engineering |  |  |  |  | X | X
1.3 | Example: Price calculation | [5 empty] | X | X | X
1.4 | Example: Cost/benefit analysis | [7 empty] | X | X
1.5 | 0
1.6 | 0
1.7 | 0
1.8 | 0
1.9 | Project management and reporting |  |  |  | X | X | X | X | X | X

## Phase 2
ACTIVITIES, BUDGET, FINANCING AND WORK SCHEDULE
One separate form to be filled in for each phase of work, but use the same work book
Write only in blue cells
Title |  | Example: Development of…
Phase of work |  | Example Phase 2:
Year and cost distribution [%]
| Last revision | 2018-04-14 | [5 empty] | 2018 | 20
| Prepared by | Petter Ola Hanssen |  |  | Tlf: | 48099548 |  | 2019 | 40
[8 empty] | 2020 | 40
[8 empty] | 2021 | 0
[8 empty] | Control | 100
Participants |  | Company A | Company B | Company C
Contact person
Phone
Mail
Hourly rate [NOK] |  | 700 | 700 | 700
Activity plan with hour budget |  | Company A | Company B | Company C | 0 | 0 | 0 | 0 | 0 | Total
| Activities | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours
1.1 | Example: Consept development | 200 | 100 | 50 | 0 | 0 | 0 | 0 | 0 | 350
1.2 | Example: Engineering | 100 | 300 | 50 | 0 | 0 | 0 | 0 | 0 | 450
1.3 | Example: Price calculation | 50 | 300 | 50 | 0 | 0 | 0 | 0 | 0 | 400
1.4 | Example: Cost/benefit analysis | 50 | 100 | 50 | 0 | 0 | 0 | 0 | 0 | 200
1.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.9 | Project management and reporting | 50 | 50 | 150 | 0 | 0 | 0 | 0 | 0 | 250
| Sum | 450 | 850 | 350 | 0 | 0 | 0 | 0 | 0 | 1650
Activity plan with cost budget |  | Company A | Company B | Company C | 0 | 0 | 0 | 0 | 0 | Total
| Activities | NOK | NOK | NOK | NOK | NOK | NOK | NOK | NOK | NOK
1.1 | Example: Consept development | 140000 | 70000 | 35000 | 0 | 0 | 0 | 0 | 0 | 245000
1.2 | Example: Engineering | 70000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 315000
1.3 | Example: Price calculation | 35000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 280000
1.4 | Example: Cost/benefit analysis | 35000 | 70000 | 35000 | 0 | 0 | 0 | 0 | 0 | 140000
1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.9 | Project management and reporting | 35000 | 35000 | 105000 | 0 | 0 | 0 | 0 | 0 | 175000
| Travel costs | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 30000
| Material costs prototype (separate specification) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Subcontracting prototype (separate specification) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Value of raw material to be destroyed after tests | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other costs (separate specification) | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 15000
| Sum | 330000 | 610000 | 260000 | 0 | 0 | 0 | 0 | 0 | 1200000
| Percentage distribution of costs | 27.5% | 50.83% | 21.67% | 0% | 0% | 0% | 0% | 0% | 100%
|  | FINANCING |  |  |  | Financing |  | Costs
[6 empty] | T | E | L | R | A |  | Distribution | Distribution
|  |  | Participants | Distribution | Own efforts | Grants | Own effort | Wages | Travel | Other |  | grants | grants
|  |  |  | of grants [%] | [%] | [NOK] | [NOK] | [NOK] | [NOK] | [NOK] |  | [NOK] | [%]
|  | 2018 | FHF | 100 |  | 120000
|  |  | IN | 0 |  | 0
|  |  | NFR | 0 |  | 0
| in Cell F68 the sum should always be 100 |  | Control | 100
|  |  | Company A |  | 50 |  | 33000 | 63000 | 2000 | 1000 |  | 33000 | 27.5
|  |  | Company B |  | 50 |  | 61000 | 119000 | 2000 | 1000 |  | 61000 | 50.8333
|  |  | Company C |  | 50 |  | 26000 | 49000 | 2000 | 1000 |  | 26000 | 21.6667
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 100
|  | 2019 | FHF | 100 |  | 240000
|  |  | IN | 0 |  | 0
|  |  | NFR | 0 |  | 0
|  |  | Control | 100
|  |  | Company A |  | 50 |  | 66000 | 126000 | 4000 | 2000 |  | 66000 | 27.5
|  |  | Company B |  | 50 |  | 122000 | 238000 | 4000 | 2000 |  | 122000 | 50.8333
|  |  | Company C |  | 50 |  | 52000 | 98000 | 4000 | 2000 |  | 52000 | 21.6667
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 100
|  | 2020 | FHF | 100 |  | 240000
|  |  | IN | 0 |  | 0
|  |  | NFR | 0 |  | 0
|  |  | Control | 100
|  |  | Company A |  | 50 |  | 66000 | 126000 | 4000 | 2000 |  | 66000 | 27.5
|  |  | Company B |  | 50 |  | 122000 | 238000 | 4000 | 2000 |  | 122000 | 50.8333
|  |  | Company C |  | 50 |  | 52000 | 98000 | 4000 | 2000 |  | 52000 | 21.6667
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 100
|  | 2021 | FHF | 100 |  | 0
|  |  | IN | 0 |  | 0
|  |  | NFR | 0 |  | 0
|  |  | Control | 100
|  |  | Company A |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | Company B |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | Company C |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0! | #DIV/0!
|  |  | Sum |  |  | 600000 | 600000 | 1155000 | 30000 | 15000 |  | 600000
|  |  | Sum grants and own effort |  |  | 1200000 | (grants + own effort)
|  |  | Sum costs |  |  | 1200000 | (wages + travel costs + other costs))
|  |  | Public support |  |  | 50%
Work Shecule
| Activities | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021
|  | 1 quarter | 2 quarter | 3 quarter | 4 quarter | 1 quarter | 2 quarter | 3 quarter | 4 quarter | 1 quarter | 2 quarter | 3 quarter | 4 quarter | 1 quarter | 2 quarter | 3 quarter | 4 quarter
1.1 | Example: Consept development |  |  |  | X | X
1.2 | Example: Engineering |  |  |  |  | X | X
1.3 | Example: Price calculation | [5 empty] | X | X | X
1.4 | Example: Cost/benefit analysis | [7 empty] | X | X
1.5 | 0
1.6 | 0
1.7 | 0
1.8 | 0
1.9 | Project management and reporting |  |  |  | X | X | X | X | X | X

## Phase 3
ACTIVITIES, BUDGET, FINANCING AND WORK SCHEDULE
One separate form to be filled in for each phase of work, but use the same work book
Write only in blue cells
Title |  | Example: Development of…
Phase of work |  | Example Phase 3
Year and cost distribution [%]
| Last revision | 2018-04-14 | [5 empty] | 2018 | 20
| Prepared by | Petter Ola Hanssen |  |  | Tlf: | 48099548 |  | 2019 | 40
[8 empty] | 2020 | 40
[8 empty] | 2021 | 0
[8 empty] | Control | 100
Participants |  | Company A | Company B | Company C
Contact person
Phone
Mail
Hourly rate [NOK] |  | 700 | 700 | 700
Activity plan with hour budget |  | Company A | Company B | Company C | 0 | 0 | 0 | 0 | 0 | Total
| Activities | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours
1.1 | Example: Consept development | 200 | 100 | 50 | 0 | 0 | 0 | 0 | 0 | 350
1.2 | Example: Engineering | 100 | 300 | 50 | 0 | 0 | 0 | 0 | 0 | 450
1.3 | Example: Price calculation | 50 | 300 | 50 | 0 | 0 | 0 | 0 | 0 | 400
1.4 | Example: Cost/benefit analysis | 50 | 100 | 50 | 0 | 0 | 0 | 0 | 0 | 200
1.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.9 | Project management and reporting | 50 | 50 | 150 | 0 | 0 | 0 | 0 | 0 | 250
| Sum | 450 | 850 | 350 | 0 | 0 | 0 | 0 | 0 | 1650
Activity plan with cost budget |  | Company A | Company B | Company C | 0 | 0 | 0 | 0 | 0 | Total
| Activities | NOK | NOK | NOK | NOK | NOK | NOK | NOK | NOK | NOK
1.1 | Example: Consept development | 140000 | 70000 | 35000 | 0 | 0 | 0 | 0 | 0 | 245000
1.2 | Example: Engineering | 70000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 315000
1.3 | Example: Price calculation | 35000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 280000
1.4 | Example: Cost/benefit analysis | 35000 | 70000 | 35000 | 0 | 0 | 0 | 0 | 0 | 140000
1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.9 | Project management and reporting | 35000 | 35000 | 105000 | 0 | 0 | 0 | 0 | 0 | 175000
| Travel costs | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 30000
| Material costs prototype (separate specification) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Subcontracting prototype (separate specification) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Value of raw material to be destroyed after tests | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other costs (separate specification) | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 15000
| Sum | 330000 | 610000 | 260000 | 0 | 0 | 0 | 0 | 0 | 1200000
| Percentage distribution of costs | 27.5% | 50.83% | 21.67% | 0% | 0% | 0% | 0% | 0% | 100%
|  | FINANCING |  |  |  | Financing |  | Costs
[6 empty] | T | E | L | R | A |  | Distribution | Distribution
|  |  | Participants | Distribution | Own efforts | Grants | Own effort | Wages | Travel | Other |  | grants | grants
|  |  |  | of grants [%] | [%] | [NOK] | [NOK] | [NOK] | [NOK] | [NOK] |  | [NOK] | [%]
|  | 2018 | FHF | 100 |  | 120000
|  |  | IN | 0 |  | 0
|  |  | NFR | 0 |  | 0
| in Cell F68 the sum should always be 100 |  | Control | 100
|  |  | Company A |  | 50 |  | 33000 | 63000 | 2000 | 1000 |  | 33000 | 27.5
|  |  | Company B |  | 50 |  | 61000 | 119000 | 2000 | 1000 |  | 61000 | 50.8333
|  |  | Company C |  | 50 |  | 26000 | 49000 | 2000 | 1000 |  | 26000 | 21.6667
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 100
|  | 2019 | FHF | 100 |  | 240000
|  |  | IN | 0 |  | 0
|  |  | NFR | 0 |  | 0
|  |  | Control | 100
|  |  | Company A |  | 50 |  | 66000 | 126000 | 4000 | 2000 |  | 66000 | 27.5
|  |  | Company B |  | 50 |  | 122000 | 238000 | 4000 | 2000 |  | 122000 | 50.8333
|  |  | Company C |  | 50 |  | 52000 | 98000 | 4000 | 2000 |  | 52000 | 21.6667
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 100
|  | 2020 | FHF | 100 |  | 240000
|  |  | IN | 0 |  | 0
|  |  | NFR | 0 |  | 0
|  |  | Control | 100
|  |  | Company A |  | 50 |  | 66000 | 126000 | 4000 | 2000 |  | 66000 | 27.5
|  |  | Company B |  | 50 |  | 122000 | 238000 | 4000 | 2000 |  | 122000 | 50.8333
|  |  | Company C |  | 50 |  | 52000 | 98000 | 4000 | 2000 |  | 52000 | 21.6667
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 100
|  | 2021 | FHF | 100 |  | 0
|  |  | IN | 0 |  | 0
|  |  | NFR | 0 |  | 0
|  |  | Control | 100
|  |  | Company A |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | Company B |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | Company C |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0! | #DIV/0!
|  |  | Sum |  |  | 600000 | 600000 | 1155000 | 30000 | 15000 |  | 600000
|  |  | Sum grants and own effort |  |  | 1200000 | (grants + own effort)
|  |  | Sum costs |  |  | 1200000 | (wages + travel costs + other costs))
|  |  | Public support |  |  | 50%
Work Shecule
| Activities | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021
|  | 1 quarter | 2 quarter | 3 quarter | 4 quarter | 1 quarter | 2 quarter | 3 quarter | 4 quarter | 1 quarter | 2 quarter | 3 quarter | 4 quarter | 1 quarter | 2 quarter | 3 quarter | 4 quarter
1.1 | Example: Consept development |  |  |  | X | X
1.2 | Example: Engineering |  |  |  |  | X | X
1.3 | Example: Price calculation | [5 empty] | X | X | X
1.4 | Example: Cost/benefit analysis | [7 empty] | X | X
1.5 | 0
1.6 | 0
1.7 | 0
1.8 | 0
1.9 | Project management and reporting |  |  |  | X | X | X | X | X | X

## Phase 4
ACTIVITIES, BUDGET, FINANCING AND WORK SCHEDULE
One separate form to be filled in for each phase of work, but use the same work book
Write only in blue cells
Title |  | Example: Development of…
Phase of work |  | Example Phase 4:
Year and cost distribution [%]
| Last revision | 2018-04-14 | [5 empty] | 2018 | 20
| Prepared by | Petter Ola Hanssen |  |  | Tlf: | 48099548 |  | 2019 | 40
[8 empty] | 2020 | 40
[8 empty] | 2021 | 0
[8 empty] | Control | 100
Participants |  | Company A | Company B | Company C
Contact person
Phone
Mail
Hourly rate [NOK] |  | 700 | 700 | 700
Activity plan with hour budget |  | Company A | Company B | Company C | 0 | 0 | 0 | 0 | 0 | Total
| Activities | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours
1.1 | Example: Consept development | 200 | 100 | 50 | 0 | 0 | 0 | 0 | 0 | 350
1.2 | Example: Engineering | 100 | 300 | 50 | 0 | 0 | 0 | 0 | 0 | 450
1.3 | Example: Price calculation | 50 | 300 | 50 | 0 | 0 | 0 | 0 | 0 | 400
1.4 | Example: Cost/benefit analysis | 50 | 100 | 50 | 0 | 0 | 0 | 0 | 0 | 200
1.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.9 | Project management and reporting | 50 | 50 | 150 | 0 | 0 | 0 | 0 | 0 | 250
| Sum | 450 | 850 | 350 | 0 | 0 | 0 | 0 | 0 | 1650
Activity plan with cost budget |  | Company A | Company B | Company C | 0 | 0 | 0 | 0 | 0 | Total
| Activities | NOK | NOK | NOK | NOK | NOK | NOK | NOK | NOK | NOK
1.1 | Example: Consept development | 140000 | 70000 | 35000 | 0 | 0 | 0 | 0 | 0 | 245000
1.2 | Example: Engineering | 70000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 315000
1.3 | Example: Price calculation | 35000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 280000
1.4 | Example: Cost/benefit analysis | 35000 | 70000 | 35000 | 0 | 0 | 0 | 0 | 0 | 140000
1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.9 | Project management and reporting | 35000 | 35000 | 105000 | 0 | 0 | 0 | 0 | 0 | 175000
| Travel costs | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 30000
| Material costs prototype (separate specification) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Subcontracting prototype (separate specification) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Value of raw material to be destroyed after tests | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other costs (separate specification) | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 15000
| Sum | 330000 | 610000 | 260000 | 0 | 0 | 0 | 0 | 0 | 1200000
| Percentage distribution of costs | 27.5% | 50.83% | 21.67% | 0% | 0% | 0% | 0% | 0% | 100%
|  | FINANCING |  |  |  | Financing |  | Costs
[6 empty] | T | E | L | R | A |  | Distribution | Distribution
|  |  | Participants | Distribution | Own efforts | Grants | Own effort | Wages | Travel | Other |  | grants | grants
|  |  |  | of grants [%] | [%] | [NOK] | [NOK] | [NOK] | [NOK] | [NOK] |  | [NOK] | [%]
|  | 2018 | FHF | 100 |  | 120000
|  |  | IN | 0 |  | 0
|  |  | NFR | 0 |  | 0
| in Cell F68 the sum should always be 100 |  | Control | 100
|  |  | Company A |  | 50 |  | 33000 | 63000 | 2000 | 1000 |  | 33000 | 27.5
|  |  | Company B |  | 50 |  | 61000 | 119000 | 2000 | 1000 |  | 61000 | 50.8333
|  |  | Company C |  | 50 |  | 26000 | 49000 | 2000 | 1000 |  | 26000 | 21.6667
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 100
|  | 2019 | FHF | 100 |  | 240000
|  |  | IN | 0 |  | 0
|  |  | NFR | 0 |  | 0
|  |  | Control | 100
|  |  | Company A |  | 50 |  | 66000 | 126000 | 4000 | 2000 |  | 66000 | 27.5
|  |  | Company B |  | 50 |  | 122000 | 238000 | 4000 | 2000 |  | 122000 | 50.8333
|  |  | Company C |  | 50 |  | 52000 | 98000 | 4000 | 2000 |  | 52000 | 21.6667
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 100
|  | 2020 | FHF | 100 |  | 240000
|  |  | IN | 0 |  | 0
|  |  | NFR | 0 |  | 0
|  |  | Control | 100
|  |  | Company A |  | 50 |  | 66000 | 126000 | 4000 | 2000 |  | 66000 | 27.5
|  |  | Company B |  | 50 |  | 122000 | 238000 | 4000 | 2000 |  | 122000 | 50.8333
|  |  | Company C |  | 50 |  | 52000 | 98000 | 4000 | 2000 |  | 52000 | 21.6667
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 100
|  | 2021 | FHF | 100 |  | 0
|  |  | IN | 0 |  | 0
|  |  | NFR | 0 |  | 0
|  |  | Control | 100
|  |  | Company A |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | Company B |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | Company C |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0! | #DIV/0!
|  |  | Sum |  |  | 600000 | 600000 | 1155000 | 30000 | 15000 |  | 600000
|  |  | Sum grants and own effort |  |  | 1200000 | (grants + own effort)
|  |  | Sum costs |  |  | 1200000 | (wages + travel costs + other costs))
|  |  | Public support |  |  | 50%
Work Shecule
| Activities | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021
|  | 1 quarter | 2 quarter | 3 quarter | 4 quarter | 1 quarter | 2 quarter | 3 quarter | 4 quarter | 1 quarter | 2 quarter | 3 quarter | 4 quarter | 1 quarter | 2 quarter | 3 quarter | 4 quarter
1.1 | Example: Consept development |  |  |  | X | X
1.2 | Example: Engineering |  |  |  |  | X | X
1.3 | Example: Price calculation | [5 empty] | X | X | X
1.4 | Example: Cost/benefit analysis | [7 empty] | X | X
1.5 | 0
1.6 | 0
1.7 | 0
1.8 | 0
1.9 | Project management and reporting |  |  |  | X | X | X | X | X | X

## Phase 5
ACTIVITIES, BUDGET, FINANCING AND WORK SCHEDULE
One separate form to be filled in for each phase of work, but use the same work book
Write only in blue cells
Title |  | Example: Development of…
Phase of work |  | Example Phase 5:
Year and cost distribution [%]
| Last revision | 2018-04-14 | [5 empty] | 2018 | 20
| Prepared by | Petter Ola Hanssen |  |  | Tlf: | 48099548 |  | 2019 | 40
[8 empty] | 2020 | 40
[8 empty] | 2021 | 0
[8 empty] | Control | 100
Participants |  | Company A | Company B | Company C
Contact person
Phone
Mail
Hourly rate [NOK] |  | 700 | 700 | 700
Activity plan with hour budget |  | Company A | Company B | Company C | 0 | 0 | 0 | 0 | 0 | Total
| Activities | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours
1.1 | Example: Consept development | 200 | 100 | 50 | 0 | 0 | 0 | 0 | 0 | 350
1.2 | Example: Engineering | 100 | 300 | 50 | 0 | 0 | 0 | 0 | 0 | 450
1.3 | Example: Price calculation | 50 | 300 | 50 | 0 | 0 | 0 | 0 | 0 | 400
1.4 | Example: Cost/benefit analysis | 50 | 100 | 50 | 0 | 0 | 0 | 0 | 0 | 200
1.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.9 | Project management and reporting | 50 | 50 | 150 | 0 | 0 | 0 | 0 | 0 | 250
| Sum | 450 | 850 | 350 | 0 | 0 | 0 | 0 | 0 | 1650
Activity plan with cost budget |  | Company A | Company B | Company C | 0 | 0 | 0 | 0 | 0 | Total
| Activities | NOK | NOK | NOK | NOK | NOK | NOK | NOK | NOK | NOK
1.1 | Example: Consept development | 140000 | 70000 | 35000 | 0 | 0 | 0 | 0 | 0 | 245000
1.2 | Example: Engineering | 70000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 315000
1.3 | Example: Price calculation | 35000 | 210000 | 35000 | 0 | 0 | 0 | 0 | 0 | 280000
1.4 | Example: Cost/benefit analysis | 35000 | 70000 | 35000 | 0 | 0 | 0 | 0 | 0 | 140000
1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.9 | Project management and reporting | 35000 | 35000 | 105000 | 0 | 0 | 0 | 0 | 0 | 175000
| Travel costs | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 30000
| Material costs prototype (separate specification) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Subcontracting prototype (separate specification) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Value of raw material to be destroyed after tests | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other costs (separate specification) | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 15000
| Sum | 330000 | 610000 | 260000 | 0 | 0 | 0 | 0 | 0 | 1200000
| Percentage distribution of costs | 27.5% | 50.83% | 21.67% | 0% | 0% | 0% | 0% | 0% | 100%
|  | FINANCING |  |  |  | Financing |  | Costs
[6 empty] | T | E | L | R | A |  | Distribution | Distribution
|  |  | Participants | Distribution | Own efforts | Grants | Own effort | Wages | Travel | Other |  | grants | grants
|  |  |  | of grants [%] | [%] | [NOK] | [NOK] | [NOK] | [NOK] | [NOK] |  | [NOK] | [%]
|  | 2018 | FHF | 100 |  | 120000
|  |  | IN | 0 |  | 0
|  |  | NFR | 0 |  | 0
| in Cell F68 the sum should always be 100 |  | Control | 100
|  |  | Company A |  | 50 |  | 33000 | 63000 | 2000 | 1000 |  | 33000 | 27.5
|  |  | Company B |  | 50 |  | 61000 | 119000 | 2000 | 1000 |  | 61000 | 50.8333
|  |  | Company C |  | 50 |  | 26000 | 49000 | 2000 | 1000 |  | 26000 | 21.6667
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 100
|  | 2019 | FHF | 100 |  | 240000
|  |  | IN | 0 |  | 0
|  |  | NFR | 0 |  | 0
|  |  | Control | 100
|  |  | Company A |  | 50 |  | 66000 | 126000 | 4000 | 2000 |  | 66000 | 27.5
|  |  | Company B |  | 50 |  | 122000 | 238000 | 4000 | 2000 |  | 122000 | 50.8333
|  |  | Company C |  | 50 |  | 52000 | 98000 | 4000 | 2000 |  | 52000 | 21.6667
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 100
|  | 2020 | FHF | 100 |  | 240000
|  |  | IN | 0 |  | 0
|  |  | NFR | 0 |  | 0
|  |  | Control | 100
|  |  | Company A |  | 50 |  | 66000 | 126000 | 4000 | 2000 |  | 66000 | 27.5
|  |  | Company B |  | 50 |  | 122000 | 238000 | 4000 | 2000 |  | 122000 | 50.8333
|  |  | Company C |  | 50 |  | 52000 | 98000 | 4000 | 2000 |  | 52000 | 21.6667
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 100
|  | 2021 | FHF | 100 |  | 0
|  |  | IN | 0 |  | 0
|  |  | NFR | 0 |  | 0
|  |  | Control | 100
|  |  | Company A |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | Company B |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | Company C |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
|  |  | 0 |  | 50 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0! | #DIV/0!
|  |  | Sum |  |  | 600000 | 600000 | 1155000 | 30000 | 15000 |  | 600000
|  |  | Sum grants and own effort |  |  | 1200000 | (grants + own effort)
|  |  | Sum costs |  |  | 1200000 | (wages + travel costs + other costs))
|  |  | Public support |  |  | 50%
Work Shecule
| Activities | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021
|  | 1 quarter | 2 quarter | 3 quarter | 4 quarter | 1 quarter | 2 quarter | 3 quarter | 4 quarter | 1 quarter | 2 quarter | 3 quarter | 4 quarter | 1 quarter | 2 quarter | 3 quarter | 4 quarter
1.1 | Example: Consept development |  |  |  | X | X
1.2 | Example: Engineering |  |  |  |  | X | X
1.3 | Example: Price calculation | [5 empty] | X | X | X
1.4 | Example: Cost/benefit analysis | [7 empty] | X | X
1.5 | 0
1.6 | 0
1.7 | 0
1.8 | 0
1.9 | Project management and reporting |  |  |  | X | X | X | X | X | X